## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Anne | 9500 | 11100 | -1600 | 4400 | 4200 | 200 | 1000 | 3000 | -2000 | 1100 | 1300 | -200 | 3000 | 2600 | 400
Bill | 9800 | 9900 | -100 | 4700 | 4200 | 500 | 1000 | 2600 | -1600 | 1100 | 1000 | 100 | 3000 | 2100 | 900
Chris | 11100 | 10200 | 900 | 6000 | 1800 | 4200 | 1000 | 2600 | -1600 | 1100 | 1500 | -400 | 3000 | 4300 | -1300
Dan | 13500 | 11600 | 1900 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 1100 | 0 | 3000 | 3500 | -500
Eric | 13500 | 11400 | 2100 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 900 | 200 | 3000 | 3500 | -500
Fran | 13500 | 11800 | 1700 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 1300 | -200 | 3000 | 3500 | -500
Total | 70900 | 66000 | 4900 | 40300 | 23400 | 16900 | 6000 | 16000 | -10000 | 6600 | 7100 | -500 | 18000 | 19500 | -1500

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Anne |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Requirements Collection | 2 | 2 | complete | key 1: complete; complete 2: complete
Repo + Git Setup | 1 | 2 | complete | this week 3: complete; planned 4: complete
Installation | 1 | 1 | complete | planned 5: complete
Music - Pre Loaded | 2 | 1 | complete | planned 6: complete
Base Sound Managment | 2 | 3 | complete | planned 7: complete; planned 8: complete; planned 9: complete
Base Sound - Obstacle Connection | 3 | 3 | complete | planned 10: complete; planned 11: complete; planned 12: complete
Testing | 4 | 4 | complete | planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
In-Depth Frequency + Obstacle Connection (Beatmap working) | 12 | 13 | complete | planned 17: complete; planned 18: complete; planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete; planned 25: complete; planned 26: complete; planned 27: complete; planned 28: complete; planned 29: complete
Integrate With Song Menu | 2 | 1 | complete | planned 30: complete
Coin/Power-up integration | 1 | 1 | complete | planned 31: complete
Documentation | 5 | 3 | this week | planned 32: this week; planned 33: this week; planned 34: this week; planned 35: this week; planned 36: this week
Further Testing | 5 | 8 | this week | planned 37: this week; planned 38: this week; planned 39: this week; planned 40: this week; planned 41: this week; planned 42: this week; planned 43: this week; planned 44: this week
Adding Patterns and Other Requirements | 4 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned
totals | 44 | 42
Bill
Requirements Collection | 2 | 3 | complete | key 1: complete; complete 2: complete; this week 3: complete
Track Design | 3 | 2 | complete | planned 4: complete; planned 5: complete
Character Design | 3 | 2 | complete | planned 6: complete; planned 7: complete
Background Design | 3 | 2 | complete | planned 8: complete; planned 9: complete
View Track Functionality | 4 | 4 | complete | planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete
View Background Functionality | 4 | 4 | complete | planned 14: complete; planned 15: complete; planned 16: complete
View Character Functionality | 4 | 3 | complete | planned 17: complete
View Obstacles Functionality | 6 | 1 | complete | planned 18: complete; planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete
Create Testing Functionality | 4 | 6 | complete | planned 24: complete; planned 25: complete; planned 26: complete; planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete; planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete; planned 37: complete; planned 38: complete
Debug Project Code | 10 | 15 | this week | planned 39: this week; planned 40: this week; planned 41: this week; planned 42: this week
Integrate With Other Components | 4 |  | planned
totals | 47 | 42
Chris
Obstacle Design | 5 | 4 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete
Obstacle Implementation | 10 | 1 | complete | planned 5: complete
Get obstacles to stick to track | 15 | 4 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete
Get obstascles to move with track. | 15 | 5 | complete | planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete
Patterns | 5 | 2 | complete | planned 15: complete; planned 16: complete
Testing | 5 | 2 | this week | planned 17: this week; planned 18: this week
Installation | 5 |  | planned | planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned
totals | 60 | 18
Dan
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
Eric (Note: Just a copy of Dan)
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
Fran (Note: Just a copy of Dan
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
group totals (hrs) | 235 | 146
group totals ($) | 23500 | 14600

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 4 | 2 | 2 | 2 | 2 | 2 | 6 | 1 | 8
Anne | 30 | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Bill | 26 | ü | ü | ü | ü | ü |  |  | ü | ü | ü
Chris | 26 | ü | ü | ü | ü |  | ü |  | ü | ü | ü
Dan | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Eric | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Fran | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Total | 160 | 6 | 24 | 12 | 12 | 4 | 4 | 8 | 36 | 6 | 48
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Anne | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6 | bar: 7 to 11
| Chapter 1 and 2, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 13
Bill | Individual schedule | 2 | 3 | bar: 1 to 2
| Champion | 5 | 2 | bar: 7 to 11
| Chapter 3 and 4, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 10
Chris | Individual schedule | 1 | 1 | bar: 1
| Champion | 5 | 8 | bar: 2 to 6
| Merge schedules on google docs | 2 | 2 | bar: 7 to 8
| Standardize formating | 1 | 1 | bar: 9
| Assemble SA Powerpoint | 2 | 3 | bar: 10 to 11
| Subtotal | 11 | 15
Dan | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Chapter 5 and 6, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 11
Eric | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 1-3 | 4 | 3 | bar: 3 to 6
| Subtotal | 11 | 9
Fran | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 4-6 | 4 | 7 | bar: 3 to 6
| Subtotal | 11 | 13
| Total | 44 | 51
red is dependent on others

## Overhead
| Anne | Bill | Chris | Dan | Eric | Fran
Training | 10 | 6 | 27 | 9 | 9 | 9
SA Preesentation Prep | 2 | 3 | 1 | 6 | 6 | 6
Software Specialist Presnetaion Prep | 1 | 2 | 2 | 1 | 1 | 1
Team Lead Presentation Prep | 4 | 6 | 3 | 7 | 7 | 7
Oral Exam Prep | 8 | 3 | 9 | 11 | 11 | 11
Post Mortum Presentation Prep | 1 | 1 | 1 | 1 | 1 | 1
Total | 26 | 21 | 43 | 35 | 35 | 35