## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Nathan | 6900 | 8000 | -1100 | 1800 | 1100 | 700 | 1000 | 3000 | -2000 | 1100 | 1300 | -200 | 3000 | 2600 | 400
Kim | 9600 | 6600 | 3000 | 4500 | 900 | 3600 | 1000 | 2600 | -1600 | 1100 | 1000 | 100 | 3000 | 2100 | 900
Scott | 9900 | 9800 | 100 | 4800 | 1400 | 3400 | 1000 | 2600 | -1600 | 1100 | 1500 | -400 | 3000 | 4300 | -1300
Matt | 8900 | 8500 | 400 | 3800 | 2100 | 1700 | 1000 | 2600 | -1600 | 1100 | 1100 | 0 | 3000 | 2700 | 300
Dawson | 13500 | 11400 | 2100 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 900 | 200 | 3000 | 3500 | -500
Total | 48800 | 44300 | 4500 | 23300 | 9900 | 13400 | 5000 | 13400 | -8400 | 5500 | 5800 | -300 | 15000 | 15200 | -200

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Nathan |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Repo + Git Setup | 1 | 1 | complete | key 1: complete
Unity Project Setup | 2 | 2 | complete | complete 2: complete
Player Manager Script | 2 | 2 | complete | this week 3: complete; planned 4: complete
Player Movement | 2 | 2 | complete | planned 5: complete
Sprites / Animations / Tileset | 4 | 4 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete
Sound Manager | 2 |  | this week | planned 10: this week; planned 11: this week
Coin/Power-up integration | 3 |  | this week | planned 12: this week; planned 13: this week; planned 14: this week
Health Bars | 2 |  | planned | planned 15: planned; planned 16: planned
totals | 18 | 11
Kim
Basic Attack Script | 2 | 2 | complete | key 1: complete
Basic Vendor System | 4 | 5 | complete | planned 4: complete; planned 5: complete
Create Currency System/ Counter | 3 | 2 | complete | planned 6: complete; planned 7: complete
Expand On Vendor Items | 8 |  | this week | planned 8: this week; planned 9: this week
Implement Dialogue | 5 |  | planned | planned 10: planned; planned 11: planned; planned 12: planned; planned 13: planned
Code boss' battles/ bullets | 10 |  | planned | planned 14: planned; planned 15: planned; planned 16: planned
Possibly Add Other Attack Types | 10 |  | planned | planned 18: planned; planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned
Possible Cutscene Creation | 3 |  | planned | planned 39: planned; planned 40: planned; planned 41: planned; planned 42: planned
totals | 45 | 9
Scott
Next Level Script | 1 | 1 | complete | key 1: complete
Chest Manager Script | 2 | 3 | complete | complete 2: complete; this week 3: complete; planned 4: complete
Level Design | 10 | 9 | complete | planned 5: complete; planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete
Obstacle Implementation | 5 | 1 | this week | bar: planned 15 to planned 19
Scene Management | 5 |  | planned | bar: planned 20 to planned 24
Audio Production | 10 |  | planned | bar: planned 25 to planned 34
Quality Insurance Testing | 15 |  | planned | bar: planned 35 to planned 49
totals | 48 | 14
Matt
Plan basic moves | 2 | 3 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Create basic detection system | 4 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
create a 'can see player function' | 2 | 1 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
create a chase player function | 1 | 1 | complete | planned 17: complete; planned 18: complete
plan patrolling system | 3 | 2 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Implement A Star Pathfinding | 5 | 6 | complete | planned 25: complete; planned 26: complete
collaborate pathfinding features | 3 | 3 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
plan searching system | 3 |  | this week | planned 31: this week; planned 32: this week; planned 33: this week; planned 34: this week; planned 35: this week; planned 36: this week
implement searching functions | 4 |  | planned | planned 37: planned; planned 38: planned; planned 39: planned; planned 40: planned
functions to interact with enviroment | 2 |  | planned | planned 41: planned; planned 42: planned
Demo Mode | 5 |  | planned | planned 43: planned; planned 44: planned
Testing | 4 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 38 | 21
Dawson
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
group totals (hrs) | 149 | 55
group totals ($) | 14900 | 5500

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 4 | 2 | 2 | 2 | 2 | 2 | 6 | 1 | 8
Nathan | 30 | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Kim | 26 | ü | ü | ü | ü | ü |  |  | ü | ü | ü
Scott | 26 | ü | ü | ü | ü |  | ü |  | ü | ü | ü
Matt | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Dawson | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Total | 134 | 5 | 20 | 10 | 10 | 4 | 4 | 6 | 30 | 5 | 40
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Nathan | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6 | bar: 7 to 11
| Chapter 1 and 2, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 13
Kim | Individual schedule | 2 | 3 | bar: 1 to 2
| Champion | 5 | 2 | bar: 7 to 11
| Chapter 3 and 4, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 10
Scott | Individual schedule | 1 | 1 | bar: 1
| Champion | 5 | 8 | bar: 2 to 6
| Merge schedules on google docs | 2 | 2 | bar: 7 to 8
| Standardize formating | 1 | 1 | bar: 9
| Assemble SA Powerpoint | 2 | 3 | bar: 10 to 11
| Subtotal | 11 | 15
Matt | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Chapter 5 and 6, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 11
Dawson | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 1-3 | 4 | 3 | bar: 3 to 6
| Subtotal | 11 | 9
| Total | 55 | 58
red is dependent on others

## Overhead
| Nathan | Kim | Scott | Matt | Dawson
Training | 10 | 6 | 27 | 8 | 9
SA Preesentation Prep | 2 | 3 | 1 | 5 | 6
Software Specialist Presnetaion Prep | 1 | 2 | 2 | 1 | 1
Team Lead Presentation Prep | 4 | 6 | 3 | 5 | 7
Oral Exam Prep | 8 | 3 | 9 | 7 | 11
Post Mortum Presentation Prep | 1 | 1 | 1 | 1 | 1
Total | 26 | 21 | 43 | 27 | 35