## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Nathan | 11200 | 8300 | 2900 | 5100 | 4000 | 1100 | 2000 | 1300 | 700 | 1100 | 1300 | -200 | 3000 | 1700 | 1300
Kim | 10600 | 6300 | 4300 | 4500 | 1800 | 2700 | 2000 | 1300 | 700 | 1100 | 1000 | 100 | 3000 | 2200 | 800
Scott | 10900 | 7500 | 3400 | 4800 | 2100 | 2700 | 2000 | 1300 | 700 | 1100 | 1100 | 0 | 3000 | 3000 | 0
Matt | 11000 | 6000 | 5000 | 4900 | 1300 | 3600 | 2000 | 1300 | 700 | 1100 | 1100 | 0 | 3000 | 2300 | 700
Dawson | 11800 | 6600 | 5200 | 5700 | 2300 | 3400 | 2000 | 1300 | 700 | 1100 | 900 | 200 | 3000 | 2100 | 900
Total | 55500 | 34700 | 20800 | 25000 | 11500 | 13500 | 10000 | 6500 | 3500 | 5500 | 5400 | 100 | 15000 | 11300 | 3700

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Nathan |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Requirements Collection | 2 | 2 | complete | key 1: complete; complete 2: complete
Repo + Git Setup | 1 | 2 | complete | this week 3: complete; planned 4: complete
Camera Movement | 3 | 3 | complete | planned 5: complete; planned 6: complete; planned 7: complete
Create Animations | 4 | 3 | complete | planned 8: complete; planned 9: complete; planned 10: complete
Player Controls | 2 | 3 | complete | planned 11: complete; planned 12: complete; planned 13: complete
Add Attack Points | 3 | 3 | complete | planned 14: complete; planned 15: complete; planned 16: complete
Make Initial Level Map | 4 | 4 | complete | planned 17: complete; planned 18: complete; planned 19: complete; planned 20: complete
NPC / item spawn points | 4 | 4 | complete
Help With Loot Drop | 2 | 3 | complete | planned 21: complete; planned 22: complete; planned 23: complete
Create Level 1 (Demo) | 3 | 3 | complete | planned 24: complete; planned 25: complete; planned 26: complete
Health Bars | 6 | 3 | this week | planned 27: this week; planned 28: this week; planned 29: this week
Make Additional Levels | 5 | 2 | this week | planned 30: this week; planned 31: this week
Music Implementation | 5 |  | planned
Make player Static | 3 | 5 | complete
Adding Patterns and Other Requirements | 4 |  | planned
totals | 51 | 40
Kim
Basic Attack Script | 2 | 2 | complete | key 1: complete
Basic Vendor System | 4 | 5 | complete | key 1: complete
Create Currency System/ Counter | 3 | 2 | complete | planned 5: complete; planned 6: complete; planned 7: complete
Expand On Vendor Items | 8 | 3 | this week | key 1: (constant); planned 8: this week
Implement Dialogue | 5 | 5 | complete | planned 16: complete
Code Boss' Battles/ Bullets | 10 | 1 | this week | key 1: this week
Possibly Add Other Attack Types | 10 |  | planned | this week 3: planned
Possible Cutscene Creation | 3 |  | planned | planned 21: planned; planned 39: planned; planned 40: planned; planned 41: planned; planned 42: planned
totals | 45 | 18
Scott
Next Level Script | 1 | 1 | complete | key 1: complete
Chest Manager Script | 2 | 3 | complete | complete 2: complete; this week 3: complete; planned 4: complete
Level Design | 10 | 9 | complete | planned 5: complete; planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete
Obstacle Implementation | 5 |  | planned | bar: planned 15 to planned 19
Scene Management | 5 |  | planned | bar: planned 20 to planned 24
Audio Production | 10 | 2 | this week | bar: planned 25 to planned 34
Quality Assurance Testing | 15 | 6 | this week | bar: planned 35 to planned 49
totals | 48 | 21
Matt
Implement A* | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Enemy Patrol/ Track | 5 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Enemy Attack | 4 | 3 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Other Melee Enemy Implementation | 10 |  | this week | planned 17: this week; planned 18: this week
Ranged Enemy Attack | 10 |  | planned | planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned; planned 24: planned
Other Enemy Improvements | 10 |  | planned | planned 25: planned; planned 26: planned
Boss mechanics(?) | 5 |  | planned | planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned
totals | 49 | 13
Dawson
Create Start Screen/Options Menu | 10 | 7 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
UI For In-Game Stats | 5 | 2 | this week | planned 8: this week; planned 9: this week; planned 10: this week; planned 11: this week; planned 12: this week
In-Game Menu | 5 | 7 | this week | planned 13: this week; planned 14: this week; planned 15: this week; planned 16: this week; planned 17: this week; planned 18: this week
Expand On Start Screen | 10 | 5 | complete | planned 19: complete; planned 20: complete
Implement Game Saves | 10 |  | planned | planned 21: planned; planned 22: planned; planned 23: planned; planned 24: planned; planned 25: planned; planned 26: planned
HighScore Display & Implmentation | 10 |  | planned | planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned; planned 31: planned; planned 32: planned
Background Enhancements & Art | 5 | 2 | this week | planned 33: this week; planned 34: this week; planned 35: this week; planned 36: this week
Dr-BC Mode | 2 |  | planned | planned 37: planned; planned 38: planned
totals | 57 | 23
group totals (hrs) | 193 | 115
group totals ($) | 19300 | 11500

## Meetings
| Date | 2021-01-14 | 2021-02-02 | 2021-02-04 | 2021-02-16 | 2021-02-20 | 2021-02-22 | 2021-03-24
| Purpose | First Meeting | Initial Game Planning | Assign Roles | Debug Features | Work on SA Pres, RFP, etc | Analysis Presentation Practice | Prepare for Weekly Status
| Hours | 1 | 1 | 2 | 2 | 3 | 2 | 2
Nathan | 13 | ü | ü | ü | ü | ü | ü | ü
Kim | 13 | ü | ü | ü | ü | ü | ü | ü
Scott | 13 | ü | ü | ü | ü | ü | ü | ü
Matt | 13 | ü | ü | ü | ü | ü | ü | ü
Dawson | 13 | ü | ü | ü | ü | ü | ü | ü
Total | 65 | 5 | 5 | 10 | 10 | 15 | 10 | 10 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Nathan | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6 | bar: 7 to 11
| Chapter 1 and 2, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 13
Kim | Individual schedule | 2 | 3 | bar: 1 to 2
| Champion | 5 | 2 | bar: 7 to 11
| Chapter 3 and 4, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 10
Scott | Individual schedule | 1 | 1 | bar: 1
| Champion | 5 | 8 | bar: 2 to 6
| Merge schedules on google docs | 2 | 2 | bar: 7 to 8
| Standardize formating | 1 | 1 | bar: 9
| Assemble SA Powerpoint | 2 | 3 | bar: 10 to 11
| Subtotal | 11 | 15
Matt | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Chapter 5 and 6, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 11
Dawson | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Main Menu | 4 | 3 | bar: 3 to 6
| Subtotal | 11 | 9
| Total | 55 | 58
red is dependent on others

## Overhead
| Nathan | Kim | Scott | Matt | Dawson
Training | 10 | 6 | 27 | 9 | 11
SA Preesentation Prep | 2 | 3 | 1 | 6 | 5
Software Specialist Presentation Prep | 1 | 7 | 2 | 1 | 1
Team Lead Presentation Prep | 4 | 6 | 3 | 7 | 4
Oral Exam Prep
Post Mortum Presentation Prep
Total | 17 | 22 | 33 | 23 | 21